# Small Language Model Jailbreak Defender

# Framework - Research Plan

Eduardo Castro Puello

Advisor: Dr. Wei Li

Every Test (OOB and FT models) will include three types of test scenarios:

Jailbreak Black Box Test:

- Direct Request, Human Jailbreak (DAN dataset), PAP-Top5

Jailbreak White Box Test:

- AutoDAN, GCG, AutoPrompt, PEZ, UAT, GBDA

Task Domain Test:

- JavaScript Library test dataset

The important milestones for this semester are marked on bold

| Task | ETA | Status |
| --- | --- | --- |
| Finish the Testing Gemma-2b-it on JavaScript dataset | Week 1 | Active |
| Black Box, White Box and JavaScript tests DeepSeek-R1 | Week 3 | Pending |
| Black Box, White Box and JavaScript tests Qwen1.5 | Week 4 | Not Started |
| Black Box, White Box and JavaScript tests Phi-3-mini | Week 5 | Not Started |
| Black Box, White Box and JavaScript tests MiniCPM-1B | Week 6 | Not Started |
| Black Box, White Box and JavaScript tests H2O-Danube-1.8B | Week 7 | Not Started |
| Report the results on the Dissertation proposal document | Week 8 | Active |
| Review Dissertation proposal with Dissertation Comite | Week 9 | Not Started |
| Black Box, White Box and JavaScript tests SmoLM-135M | Week 10 | Not Started |
| Present Dissertation proposal with the Dissertation Comite | Week 11-12 | Not Started |
| Black Box, White Box and JavaScript tests StableLM-2-Zephyr | Week 11 | Not Started |
| Black Box, White Box and JavaScript tests MobileLLaMA-1.4B | Week 12 | Not Started |
| Black Box, White Box and JavaScript tests Fox-1-1.6B | Week 13 | Not Started |
| Black Box, White Box and JavaScript tests Dolly-v1-6b | Week 14 | Not Started |
| Black Box, White Box and JavaScript tests OLMo-7B | Week 15 | Not Started |
| Report results on the dissertation document | Week 16 | Not Started |
| Refine dissertation document | Week 20 | Not Started |